## Summary
CrankMagic UAT — 2026-09-21 (amended: + Explore live Personal-HP)
App: C:\Users\robmi\CrankMagic\repo / box mirror #311. Design gallery. Play IN FLUX (Claude). ZERO code by Grok agents.
New S2 from executor: L-02 Sheet cells not editable; E-01b Discover cold load vs Gallery Explore entry. D-03b Fail S3 rail Ready to add / Make the change.
Explore live on :8790 added. Totals now ~110 cases. New open: EXP-J4-01 Wanted/To-buy handoff; EXP-J2-01 facet visibility; EXP-J1-01 deck-scoped path needs seed.
Core function | Cases | Pass | Pass after fix | Partial | Fail | Not run | Open S1 | Open S2
Build | 23 | 17 | 0 | 5 | 1 | 0 | 0 | 0
Acquire | 5 | 4 | 0 | 0 | 1 | 0 | 0 | 1
Manage | 20 | 10 | 0 | 4 | 4 | 2 | 0 | 1
Play | 17 | 4 | 0 | 1 | 5 | 7 | 4 | 3
Design | 30 | 13 | 0 | 9 | 6 | 2 | 0 | 9
Total | 95 | 48 | 0 | 19 | 17 | 11
Severity: S1 blocks/corrupts · S2 wrong data / cannot complete intended way · S3 friction · S4 cosmetic
Ops Play blockers: JDK commander-runtime ENOENT; cloudflared/guestOrigin; Desktop vs repo dual path (DR-P09).

## Test Cases
ID | Core function | Use case | Steps | Expected behavior | Experienced behavior | Result | Severity | Evidence (screenshot) | Recommended remediation | Code location | Status | Source
UAT-GUEST-01 | Play | Open human lobby for remote guests | POST /api/start LobbyPack with human seats | Lobby opens; invites mintable | 400 Remote guests unavailable — restart with Remote Guests enabled | Fail | S1 | Hosted Play | Restart host via Desktop shortcut with -RemoteGuests; ensure cloudflared https | game/tools serve / launch ps1 | Open — ops | Hosted Play
UAT-START-02 | Play | Host+3AI Start→Forge | POST start after prepare | Forge JVM launches; /api/live ready/playing | 400 spawnSync javac.exe ENOENT — C:\Users\robmi\CrankMagic\commander-runtime\jdk-17... missing; live idle | Fail | S1 | Hosted Play | Restore commander-runtime JDK under CrankMagic (or retarget path to runtime\jdk-17.0.20.1+1 which exists under workbench/runtime); then re-Start | Forge spawn path config | Open — ops | Hosted Play
CM-DS-004 | Design | No navy surfaces | Scan design.css for navy covers | Blue only mist/focus/Explore | Brass dominates live; design.css still ships navy v-cover gradients | Fail | S2 | Workshop Design | Delete dead Deep-Field navy CSS so it cannot paint | crankmagic-design.css | Open | Workshop Design
CM-DS-005 | Design | Focus ring aether | Tab focus controls | 2px --color-aether focus | :focus-visible uses brass accent | Fail | S2 | Workshop Design | Set focus-visible to --color-aether | crankmagic-design.css :focus-visible | Open | Workshop Design
CM-DS-009 | Design | Library primary control height | Library head actions | Add cards primary 42px | Hierarchy OK but .compact 32px | Fail | S2 | Workshop Design | Drop .compact on Library head; use 42px Gallery control height | crankmagic-collection.js / CSS .compact | Open | Workshop Design
CM-DS-010 | Design | Decks grid 3-col | Decks grid | 3-col gap 20; tiles 3:4 r22 | auto-fill minmax(260px,1fr) — density diverges | Fail | S2 | Workshop Design | Lock grid-template-columns: repeat(3, minmax(0,1fr)) at desktop | crankmagic.css deck tiles grid | Open | Workshop Design
CM-DS-012 | Design | Library type/spacing scale | Library filters/actions | 42px filters/actions | head+row .compact 32px undershoot | Fail | S2 | Workshop Design | Restore 42px control scale on Library chrome | crankmagic.css .compact | Open | Workshop Design
DR-P09 | Play | Dual path Desktop shortcut vs CrankMagic\repo | Compare Desktop Start Game target vs repo tree | One canonical Online tree | Desktop vs repo dual path risk | Fail | S2 | Play Design | Unify: shortcut WorkingDirectory → C:\Users\robmi\CrankMagic\repo (or document single path); retire commander-phase-c if obsolete | Start Game.lnk; launch ps1 | Open — IN FLUX | Play Design
E-01b | Design | Explore route naming / cold load | Revisit #discover (finish walk) |  |  | Fail | S2 | app-explore-seeded2.png | Keep Explore entry as default when no focus; rename Discover→Explore in pageHead/HELP; show entry while graph warms or progress on entry chrome | crankmagic-discover.js views.discover pageHead("Discover") | Open | Executor Decks/Library
L-02 | Manage | Sheet view editable numeric cells | Library → Sheet view |  |  | Fail | S2 | app-library-sheet2.png | Implement in-place numeric editors per Gallery Sheet behaviour (inputmode=numeric, commit on Enter/Tab) | crankmagic-collection.js sheet view; crankmagic.css sheet cells | Open | Executor Decks/Library
LIB-06 | Acquire | Wanted on To buy tab (Design C) | Add Wanted; open To buy; check badge + KPI | To buy = shortfalls AND Wanted; Wanted not Watched | Shop filter excludes kind=entry; buy count = need only; entry counted as Watched | Fail | S2 | rows/tabCounts/statsHTML; Design C | Design C: include want-list (group:to-buy entry) lots in To buy shop filter + buy tab/KPI counts; do NOT rename UI to Wanted for Gallery — Gallery/wireframes use To buy / Buy list only (0 hits for Wanted). | crankmagic-collection.js rows/tabCounts/statsHTML | Open | Collection truth
UAT-ENV-02 | Play | guestOrigin https for remote guests | Check /api setup guestOrigin + cloudflared | https guestOrigin; remoteGuestsAvailable true | guestOrigin=http://127.0.0.1:8769; cloudflared not running; remoteGuestsAvailable=false | Fail | S2 | Hosted Play | Relaunch Desktop Start Game with Remote Guests so cloudflared publishes https guestOrigin | launch-crankmagic-online.ps1 -RemoteGuests | Open — ops | Hosted Play
D-03b | Build | Rail sub-pages Ready to add / Make the change under open deck | With deck open, inspect rail under that deck |  |  | Fail | S3 | app-deck-krenko-overview.png; app-ready-to-add.png; app-make-the-change.png | Render C.SUBNAV.decks Ready to add / Make the change indented under current deck in rail on all deck tabs | crankmagic-decks.js C.SUBNAV.decks; index.html rail render | Open | Executor Decks/Library
DR-P06 | Play | Change deck 2d tabs Saved/Lab/Bring + Use-at-Seat | Open Change deck flow vs wireframe 2d | Tabs Saved/Lab/Bring + Use-at-Seat | Not matching 2d | Fail | S3 | Play Design | Implement Change deck 2d structure (Claude Play lane) | crankmagic-game.js change deck | Open — IN FLUX | Play Design
LIB-01 | Manage | Library head actions | Open #cards Library | Import list · More ▾ · primary Add cards (primary rightmost) | pageHead order is Add cards (primary) · Import list · More | Fail | S3 | Collection truth source | Reorder head buttons to match Gallery Library | crankmagic-collection.js cardsHead | Open | Collection truth
LIB-04 | Manage | Card cell mana marks | Library List Card column | Color-identity pips + land L before name | rowMark uses mana COST not identity; land L OK | Fail | S3 | rowMark vs Gallery | Render identity pips per gallery; keep land mark | crankmagic-collection.js rowMark | Open | Collection truth
W-DECKS-04 | Manage | Read Decks rail subnav | Open Decks empty state | Full “How a deck comes together” (or Gallery-equivalent) readable | Rail sub-link truncates to “How a deck comes to…” | Fail | S3 | /workspace/uat/findings/live-decks.png | Widen rail / wrap / shorten label; verify at 216px | index.html + CSS rail | Open | Workshop IA
CM-DS-001 | Design | Shell rail structure | Compare Decks/Deck/Library shell to Gallery | 216px rail; no top header; logo+aether; Decks·Library·Explore·Play; Menu foot | Structure OK; wordmark CrankOxanium vs Gallery Satoshi; dead .v-top/.v-layout{150px} CSS; subnav hover #fff | Partial | S2 | Workshop Design | Remove dead Deep-Field/v-* CSS; align wordmark font to Gallery Satoshi; fix subnav hover | crankmagic-design.css; index.html shell | Open | Workshop Design
CM-DS-011 | Design | Deck page h1 / bento | Deck Overview | Hero h1 56; bento 6-col | Largely matches; global h1 36/700 still in design.css (override race) | Partial | S2 | Workshop Design | Remove dead global h1 36/700 rule | crankmagic-design.css h1 | Open | Workshop Design
DR-P05 | Play | Center table tools: End table / force-advance | Inspect center Table rules / Host tools | End table + force-advance per DELTA/wireframe Host tools | Still has Start/Stop; missing End table/force-advance | Partial | S2 | Play Design | Align Host tools to DELTA: End table + force-advance; clarify Start/Stop vs auto-launch | crankmagic-game.js host tools | Open — IN FLUX | Play Design
CM-DS-002 | Design | Shell <760 phone | Narrow viewport | Rail→top row; sticky 46px bottom deck actions | Horizontal sticky sidebar; current ≠ raised pill; 46px trio not verified | Partial | S3 | Workshop Design | Match Gallery phone current=raised; verify sticky trio | crankmagic.css shell media | Open | Workshop Design
D-01b | Build | Deck tiles + New deck primary + Compare | On #decks inspect grid, New deck, Compare |  |  | Partial | S3 | app-decks-populated.png; gal-decks.png | Pin Decks grid to repeat(3, minmax(0,1fr)) at desktop; rename Compare to match Gallery or keep selected-count pattern but show enabled secondary when ≥2 picks; radius 22px | crankmagic.css .cm-deck-grid {repeat(auto-fill,minmax(260px,1fr))} | Open | Executor Decks/Library
DR-P02 | Design | Lobby geometry 2×2 vs legacy card-row PNGs | Compare live repo lobby to wireframe 2b vs old UAT PNGs | Quadrant 2×2 table-first lobby per 2b | Repo has 2b slice; older PNGs still card-row — dual visual truth | Partial | S3 | Play Design | Retire/archive card-row UAT shots; single geometry source of truth | crankmagic-game.js lobby layout | Open — IN FLUX | Play Design
DR-P03 | Design | Seat chrome commander-forward vs under-bars hero | Compare seat chrome to Gallery/DELTA | Commander-forward seat chrome per current design | Under-bars hero path still present in older artifacts | Partial | S3 | Play Design | Confirm with Trey whether under-bars/Deck Summary still locked; else treat as legacy | crankmagic-game.js seat render | Open — IN FLUX | Play Design
L-06 | Manage | Cross-surface count vocabulary | Compare Library summary vs KPI tiles vs Gallery sample figures |  |  | Partial | S3 | app-library-seeded2.png; gal-library.png | Align head sentence with KPI definitions (or footnote what "copies you own" includes) | crankmagic-collection.js pageHead / counters | Open | Executor Decks/Library
M-LIVE-1 | Build | Live browser Measure walk | HTTP servers + Playwright | Full SPA Measure click walk | :8768/:8769 200; Playwright walk not run (node not on Shell PATH) | Partial | S3 | Measure | Optional live click walk when Playwright available |  | Open | Measure
UAT-DELTA-01 | Design | DELTA B.5 No Launch vs live Start+countdown | Compare DELTA to live + Claude batch 5.2 | DELTA: auto 10s when ready, no Launch | Live has Start + countdown (Rob request per Claude) — intentional product delta vs wireframe | Partial | S3 | DELTA-play; docs/uat-lobby | Update DELTA/wireframe to match locked Start+countdown OR revert UI to auto-launch — Trey decide | docs/design DELTA §B.5 | Open — product decision | Hosted Play
W-DECKS-02 | Manage | Compare two decks | Decks list → Compare | Gallery: Compare secondary + New deck primary in page head | Gallery Decks head shows Compare (secondary) + New deck (primary) over 3-col poster grid (gallery-decks.png). Live empty Decks has New deck + Import a backup only (no Compare). Live with decks uses Compare selected (checkbox-gated). | Partial | S3 | /workspace/uat/findings/gallery-decks.png;/workspace/uat/findings/live-decks.png | Align Decks head actions to Gallery Compare + New deck hierarchy; keep multi-select if needed | crankmagic-decks.js pageHead | Open | Workshop IA
W-DECKS-03 | Manage | Scan deck library tiles | View Decks grid | 3-col 3:4 poster tiles; stage pill; mana pips; readiness; dashed + New deck; hover lift; Brass tint | Gallery Decks = 3-col posters + Compare + New deck + summary line (gallery-decks.png). Live empty = hero “Build it. Make it yours.” + New deck / Import a backup + card fan (live-decks.png). No live populated Decks grid shot yet. | Partial | S3 | /workspace/uat/findings/live-decks.png;/workspace/uat/findings/gallery-decks.png | Screenshot side-by-side with Gallery Decks.dc.html at 1280px; close spacing/radius gaps | crankmagic-decks.js views.decks + CSS tiles | Open | Workshop IA
W-DECKS-05 | Build | Empty Decks first-run | Open Decks with zero decks | Gallery shows poster grid (or empty that still teaches tiles); primary New deck | Gallery Decks = 3-col posters + Compare + New deck + summary line (gallery-decks.png). Live empty = hero “Build it. Make it yours.” + New deck / Import a backup + card fan (live-decks.png). No live populated Decks grid shot yet. | Partial | S3 | /workspace/uat/findings/live-decks.png;/workspace/uat/findings/gallery-decks.png | Reconcile empty state with Gallery empty/populated patterns | crankmagic-decks.js empty showcase | Open | Workshop IA
W-DS-01 | Manage | Design-system palette | Inspect CSS tokens vs Gallery Brass & Slate | Tokens #1a1815 / #231f1b / accent #d9a441; Young Serif display; no navy primary | Live deck page + Decks empty use warm brass primary (#d9a441-class) on near-black brown; Gallery matches. CSS still has leftover hex sweep work; no navy primary chrome in these shots (logo wand blue only). | Partial | S3 | /workspace/uat/findings/live-deck-page.png;/workspace/uat/findings/gallery-deck-page.png;/workspace/uat/findings/live-decks.png | Finish literal→token sweep; accept DoD screenshots vs Gallery | crankmagic.css / crankmagic-design.css | Open | Workshop IA
W-PAGE-02 | Build | Overview bento next-step | Open Overview on a deck | Gallery bento: NEXT · PROGRESS · COST (+ more tiles when populated) | Live Krenko draft Overview shows NEXT / PROGRESS / COST bento; commander art missing (broken image) on brand-new draft; Gallery shows full art + richer NEXT copy for populated deck | Partial | S3 | /workspace/uat/findings/live-deck-page.png;/workspace/uat/findings/gallery-deck-page.png | Ensure commander art resolves on Create draft; keep bento structure; polish NEXT copy for Defining vs Playable states | crankmagic-decks.js overview + card image resolve | Open | Workshop IA
A-00 | Design | Empty Decks landing before Load Live | Fresh browser profile → #decks before Load Live |  |  | Partial | S4 | app-decks-landing.png | Optional empty-state notes in handoff; ensure Load Live discoverable (Menu path works) | crankmagic-decks.js empty branch | Open | Executor Decks/Library
D-08 | Build | Compare decks affordance | Inspect Compare on Decks landing |  |  | Partial | S4 | app-decks-populated.png; gal-decks.png | Match Gallery label "Compare"; allow entry to compare flow or explain disabled state in UI | crankmagic-decks.js compare control | Open | Executor Decks/Library
DR-P07 | Design | Choose mat depth | Inspect Choose mat | Mat chooser depth per Sea Options / 2b | Partial depth | Partial | S4 | Play Design | Deepen Choose mat to wireframe options | crankmagic-game.js mat | Open — IN FLUX | Play Design
DR-P08 | Design | Shell Brass/Slate vs residual navy | Compare tokens vs old shots | Brass & Slate tokens throughout Play chrome | Residual navy on older shots; live may be partial | Partial | S4 | Play Design | Sweep Play chrome for leftover navy; apply design-system tokens | crankmagic.css / crankmagic-design.css | Open | Play Design
UAT-DELTA-03 | Play | DELTA C–D table/Focus chrome | Enter live game | Table chrome per DELTA | Not reached — Forge never launched | Not run | S1 | Hosted Play | Unblock UAT-START-02 first | game/ui/review.* | Open — blocked | Hosted Play
UAT-GUEST-02 | Play | Fresh #table=&invite= guest link | Mint invite after human lobby | https URL with table+invite | Blocked by UAT-GUEST-01 | Not run | S1 | Hosted Play | Unblock guestOrigin first |  | Open — ops | Hosted Play
LIB-11 | Design | Gallery chrome pixels | Compare live to Gallery Library.dc.html | Young Serif, brass primary, 7 tiles, page-size 60/120/All | Gallery HTML did not paint in box Chrome (support.js React unpkg ERR_TUNNEL). Expectations from source only. Live pager Prev/Next; prefs have 60/120/All. Not a product visual contradict. | Not run | S2 | Pending screenshots | Optional: expose 60/120/All page-size segment like Gallery footer; keep LIB-11 Open as incomplete visual compare (infra), not defect | crankmagic-design.css / cardsHead | Open | Collection truth
E-BLOCK-01 | Manage | Explore live Personal-HP walk (agent) | Discover sample filters/chains | Live Explore UAT on Personal-HP | Explore agent blocked; box executor covered E-01b on seeded Load Live instead | Not run | S3 | explore-discover-uat-2026-09-21.md | Optional follow-up Explore deep sample on HP | crankmagic-discover.js | Open | Explore
UAT-DELTA-02 | Design | DELTA B.4 Choose mat / fan / quadrant sea | Visual verify | Mats/sea/overlap per DELTA | Claude claims done; Hosted Play no CDP re-verify | Not run | S3 | Claude uat-lobby | Visual re-verify with CDP | crankmagic-game.js | Open — IN FLUX | Hosted Play
UAT-ENV-04 | Play | CDP :9222 browser drive | Attach Playwright/CDP | UI automation available | timeout — no CDP browser | Not run | S3 | Hosted Play | Attach Chrome with --remote-debugging-port=9222 or install Playwright for Cursor helper |  | Open — ops | Hosted Play
UAT-WF-02 | Play | lobby-permutations Playwright | Run lobby permutation suite | Seat role permutations covered | Playwright not installed in Cursor node helper | Not run | S3 | Hosted Play | Install Playwright in UAT helper or use Claude prior green log as provisional |  | Open — ops | Hosted Play
W-DS-02 | Manage | Shell structure | Compare shell to Gallery | 216px rail; logo in rail; Menu ▾ foot; no top header bar | Live still uses cm-layout 216px rail — full Gallery shell (Menu foot / header removal) Not run pending screenshot | Not run | S3 | /workspace/uat/findings/(pending live-shell.png) | Screenshot shell vs Gallery; implement remaining shell steps from IMPLEMENTATION-GUIDE §2 | index.html + crankmagic.css shell | Open | Workshop IA
W-PLAY-01 | Play | Play entry from Decks domain | Click Play | IN FLUX — test what is there; mark IN FLUX; do not fight commits | Out of Workshop deep UAT this pass (Play>Lobby>Game owned elsewhere); nav label Play present | Not run | S4 | n/a | Defer to Play/Hosted Play UAT lanes | Play routes | Open | Workshop IA
DR-P10 | Play | Table 2e/2f live canvas | Play through table wireframes | 2e/2f game canvas conformance | Not run (IN FLUX / Forge session) | Not run |  | Play Design | Re-run after Claude Play merge + Forge available | game/ui/review.* | Open — IN FLUX | Play Design
UAT-SEAT-01 | Play | Human/AI/Unused seat UI | Drive lobby UI | Role controls work | NOT DRIVEN (no CDP); Claude log claimed prior green | Not run |  | docs/uat-lobby-2026-09-21.md | Re-drive when CDP available | crankmagic-game.js | Open — IN FLUX | Hosted Play
D-04 | Build | The hundred / Upgrades / Acquire / Explore tabs | Visit #decks?deck=deck:live:D6&tab=hundred¦upgrades¦acquire¦explore |  |  | Pass | S3 | app-deck-hundred.png; app-deck-upgrades.png; app-deck-acquire.png; app-deck-explore.png | Follow-up UAT vs wireframes turn 1a–1c for row density / Open in Library links | crankmagic-decks.js tab renderers | Open | Executor Decks/Library
A-01 | Design | Menu / Share / Feedback / Tour | Open rail Menu |  |  | Pass | S4 | app-menu-open2.png | None | index.html #cm-user-menu | Open | Executor Decks/Library
A-02 | Design | Theme tokens Brass & Slate / Felt & Cream | Measure CSS vars; toggle theme |  |  | Pass | S4 | app-theme-light2.png; app-decks-populated.png | None | crankmagic-design.css #matrix-v2 tokens | Open | Executor Decks/Library
A-03 | Manage | Encoding / persistence after reload | Reload #decks after Load Live |  |  | Pass | S4 | app-decks-reload-seeded.png | None | collection-repository.js IndexedDB | Open | Executor Decks/Library
CM-DS-003 | Design | Tokens Brass & Slate hex | Compare --color-* to handoff | Dark/light hex set match | --color-* matches; dual --v-* aliases; light theme OK | Pass | S4 | Workshop Design | Consolidate --v-* / poster-* namespaces | crankmagic-design.css tokens | Open | Workshop Design
CM-DS-007 | Design | Deck Overview primary | Overview Next bento | One accent fill (DoD); Gallery Next also fills buy CTA | Hero one primary; Next text-only — live matches written DoD better than Gallery mock | Pass | S4 | Workshop Design | Optional: update Gallery Next to match DoD one-primary | crankmagic-decks.js overview | Closed | Workshop Design
D-00 | Build | Load Live seeds UAT collection | Menu → Load Live → password → Replace library |  |  | Pass | S4 | app-decks-after-live2.png; app-load-live-review2.png | None (UAT harness step) | crankmagic-exchange-ui.js load-live | Open | Executor Decks/Library
D-01a | Design | Decks landing shell matches Gallery Decks | Load Live → #decks; compare to Gallery Decks.dc.html |  |  | Pass | S4 | app-decks-populated.png; gal-decks.png | None | crankmagic-decks.js views.decks; crankmagic-design.css tokens | Open | Executor Decks/Library
D-02 | Build | New deck Create / Import / Lab doors | Click primary New deck |  |  | Pass | S4 | app-new-deck-doors2.png | None | crankmagic-decks.js new-deck action | Open | Executor Decks/Library
D-03a | Build | Deck Overview vs Gallery Deck Page | Open D6 Krenko from rail; inspect Overview |  |  | Pass | S4 | app-deck-krenko-overview.png; app-deck-overview-seeded.png; gal-deck-page.png | None | crankmagic-decks.js overview() | Open | Executor Decks/Library
D-05 | Manage | Ready to add + Make the change surfaces | Open #pull?deck=deck:live:D6 and #change?deck=deck:live:D6 |  |  | Pass | S4 | app-ready-to-add.png; app-make-the-change.png | None | crankmagic-decks.js pull/change views | Open | Executor Decks/Library
E-01a | Design | Explore entry vs Gallery Explore Entry | Cold navigate #discover after Load Live (first seeded shot) |  |  | Pass | S4 | app-explore-seeded.png; gal-explore-entry.png | None | crankmagic-discover.js entry | Open | Executor Decks/Library
L-01 | Acquire | Library head + status KPI tiles vs Gallery Library | #cards after Load Live |  |  | Pass | S4 | app-library-seeded2.png; gal-library.png | None | crankmagic-collection.js | Open | Executor Decks/Library
L-03 | Acquire | To buy + Orders flows sample | #cards?tab=buy and #cards?tab=orders |  |  | Pass | S4 | app-library-tobuy2.png; app-library-orders.png | None | crankmagic-collection.js buy/orders tabs | Open | Executor Decks/Library
LIB-03 | Manage | KPI status tiles | Library List; read 7 count tiles | Seven gallery KPIs; click filters | Same seven; minor title-case Physical Deck / To Buy | Pass | S4 | STAT_FIGURES | Optional casing align | crankmagic-collection.js STAT_FIGURES | Closed | Collection truth
LIB-07 | Acquire | Acquire for a deck journey | Deck Buy list → Bought/Ordered → Library To buy/Orders | One-tap Bought/Arrived; order dialog | IA present; Acquire chrome wireframe-only hi-fi | Pass | S4 | shop-*; wireframe 1c/4d | Visual chrome Acquire deferred | crankmagic-collection.js / crankmagic-orders.js | Closed | Collection truth
LIB-08 | Manage | Upgrades / substitutes | Substitute → To bench; Ready to add Swap | To bench; Ready to add lists substitutes | Verb present; pull.js not walked live | Pass | S4 | primary Substitute | Live Ready-to-add visual sample still Open | crankmagic-collection.js; crankmagic-pull.js | Open | Collection truth
LIB-10 | Manage | Table view sample | Library view Table | Piles on mat; Wanted pile if any | Wired; not hi-fi; visual pending | Pass | S4 | tabletop.js | Visual sample pending | crankmagic-tabletop.js | Open | Collection truth
W-DECKS-01 | Build | Start a new deck from Decks | Decks → New deck | Primary New deck; wizard Create · Import · Lab | new-deck modal offers wizard-create / wizard-import / wizard-lab | Pass | S4 | /workspace/uat/app/crankmagic-decks.js (New deck modal ~468) | None | crankmagic-decks.js actions new-deck/wizard-* | Open | Workshop IA
W-LAB-01 | Build | Lab auto-build from New deck | New deck → Lab | Lab path opens Deck Lab build-100 (CrankDraft) | wizard-lab navigates to Lab; CrankDraft.build is shared engine (Hosted Play lobby also) | Pass | S4 | /workspace/uat/app/crankmagic-decks.js wizard-lab; draft-builder.js | None — do not fork builder | wizard-lab + draft-builder.js | Open | Workshop IA
W-LAB-02 | Build | Create vs Import paths | New deck → Create / Import | Create commander picker; Import list paste/file | wizard-create and wizard-import present | Pass | S4 | /workspace/uat/app/crankmagic-decks.js | Live walk empty/error states still Not run | wizard-create/import | Open | Workshop IA
W-NAV-01 | Manage | Open app shell | Load index.html; read top/side nav | Gallery: Decks · Library · Explore · Play | Live tip #311 index.html data-nav labels are Decks / Library / Explore / Play (hashes decks/cards/discover/game) | Pass | S4 | /workspace/uat/app/index.html | None — matches Gallery IA | index.html nav | Open | Workshop IA
W-PAGE-01 | Manage | Open deck hub tabs | Open a deck | Tabs Overview · The hundred · Upgrades · Acquire (Measure as action) | Live and Gallery Deck Page both show Overview · The hundred · Upgrades · Explore · Acquire; Measure is an action button on both (live-deck-page.png vs gallery-deck-page.png). | Pass | S4 | /workspace/uat/findings/live-deck-page.png;/workspace/uat/findings/gallery-deck-page.png | Confirm with design whether deck-scoped Explore tab stays (Phase 1 handoff) or Gallery tab strip wins | crankmagic-decks.js DECK_TABS | Open | Workshop IA
W-PAGE-03 | Acquire | Buy remaining cards | Open Acquire tab | Acquire buy list / ordered / $ to finish (Gallery Acquire) | Acquire section uses To buy · Ordered · $ to finish — aligns Design C shortfalls=To buy (not Wanted) | Pass | S4 | /workspace/uat/app/crankmagic-decks.js acquire renderer | None | crankmagic-decks.js acquire | Open | Workshop IA
W-PAGE-04 | Build | Measure / refine list | Deck page Measure control | Measure as action with fidelity honesty (model≠rules engine) | measure-deck button title states browser simulation model not full rules engine | Pass | S4 | /workspace/uat/app/crankmagic-decks.js ~204 | None | crankmagic-decks.js measure-deck | Open | Workshop IA
CM-DS-006 | Design | Decks primary one/view | Decks head | New deck brass; Compare outlined | Matches | Pass |  | Workshop Design |  | crankmagic-decks.js pageHead | Closed | Workshop Design
CM-DS-008 | Design | Deck Explore tab primary | Explore tab | One primary | Open Discover primary; Measure/More outlined OK | Pass |  | Workshop Design |  |  | Closed | Workshop Design
DR-P01 | Design | IN FLUX flag — Claude owns Play Lobby→Game | Note mandate | Play domain treated as in flux during UAT | Flagged; no code | Pass |  | Play Design report | Keep Play UAT advisory until Claude merge settles |  | Open | Play Design
DR-P04 | Design | Own-quadrant actions | Inspect seat quadrant actions | Actions scoped to own quadrant | Present in 2b slice | Pass |  | Play Design |  |  | Open — IN FLUX | Play Design
LIB-02 | Manage | Tabs + views | Open Library; switch tabs/views | Tabs Library · To buy · Orders; views List · Sheet · Table; Sheet library-only | Matches; Table=tabletop | Pass |  | Collection truth |  | crankmagic-collection.js viewSwitch | Closed | Collection truth
LIB-05 | Manage | Purpose chip + verbs | Library List sample statuses | Purpose chip; verbs Bought/Arrived/To bench/Reserve; physical deck no verb | Matches + Put in Dx for reserved-not-boxed | Pass |  | primary/rowHTML |  | crankmagic-collection.js | Closed | Collection truth
LIB-09 | Manage | Status changes | Row Status menu / Sheet edit | Status ladder; Sheet editable | Present | Pass |  | statusMenu |  | collection + css | Closed | Collection truth
M-CTA-1 | Build | Deck hero Measure CTA + honesty tooltip | Open deck Overview | Measure / Measure again + honesty title | Present | Pass |  | crankmagic-decks.js |  | crankmagic-decks.js hero Measure | Closed | Measure
M-CTA-2 | Design | Measure button in deck actions | Inspect hero actions | v-button in cm-deck-actions | Present | Pass |  | decks.js |  | crankmagic-decks.js | Closed | Measure
M-CTA-3 | Build | Measure hidden when archived/empty | Archived or no cards | Measure hidden | Gate d.archived¦¦!cards.length | Pass |  | decks.js |  | crankmagic-decks.js | Closed | Measure
M-CTA-4 | Design | Measure CTA tokenized colors | Inspect CSS + design-tokens tests | Tokenized .v-button; no hard-coded colors | design-tokens.mjs 62 passed | Pass |  | tests/design-tokens.mjs |  | crankmagic-design.css | Closed | Measure
M-FID-1 | Build | Lab report fidelity banner | Open Lab measurement report | Banner: browser model, not full rules, not real-evening prediction | fidelityBanner exact string present | Pass |  | crankmagic-lab.js |  | crankmagic-lab.js fidelityBanner | Closed | Measure
M-FID-2 | Build | Lab protocol chip 120k | Read Lab report chip | Published protocol · 120,000 games | Chip + PROTOCOLS.published 6×20k | Pass |  | lab + CrankSim |  | crankmagic-lab.js; crankmagic-sim.js | Closed | Measure
M-FID-3 | Build | Lab aside refine vs published counts | Read Lab aside | Refine 3×4k (12k); published 6×20k / 120k | Matches | Pass |  | Lab aside |  | crankmagic-lab.js | Closed | Measure
M-FID-4 | Build | HELP.lab fidelity copy | Read HELP.lab | Simulated games under model; no calibrated-human claims | Matches | Pass |  | HELP.lab |  | HELP.lab | Closed | Measure
M-RPT-1 | Build | measurePublished API 120k published-only | Inspect export | C.measurePublished / CrankSim.measurePublished | Export present; full 120k not executed this UAT | Pass |  | Measure | Optional live 120k smoke later | crankmagic-lab.js / crankmagic-sim.js | Closed | Measure
M-RPT-2 | Build | packFor report contract | Unit tests | protocol, deckFingerprint, limits honesty | tests/crankmagic-sim.mjs 36 passed | Pass |  | unit tests |  | crankmagic-sim.js | Closed | Measure
M-RPT-3 | Build | Attach handoff ownership | Inspect attach path | Measure returns {report}; Collection attachDeckReport | Matches | Pass |  | Measure |  | collection-lobby-draft / attachDeckReport | Closed | Measure
UAT-DECK-01 | Play | Library live D1–D6 in setup catalog | GET /api/setup | D1–D6 commanders listed | Listed ok | Pass |  | Hosted Play |  |  | Closed | Hosted Play
UAT-ENV-01 | Play | Host up :8768 | GET /app | 200 | 200; /api/setup decks=207 incl D1–D6 | Pass |  | Hosted Play API |  |  | Closed | Hosted Play
UAT-ENV-03 | Play | desktop-deks API | GET /api/desktop-deks | Six D1–D6 decks with tokens | 6 decks with token | Pass |  | Hosted Play |  |  | Closed | Hosted Play
UAT-START-01 | Play | Host+3AI prepare | POST prepare Host+3AI | CommanderPodPack issued | prepare ok @1 id issued | Pass |  | Hosted Play |  |  | Closed | Hosted Play
UAT-WF-01 | Design | wireframe-conformance suite | Run wireframe-conformance tests | All checks green | 38/38 PASS | Pass |  | Hosted Play |  | tests/wireframe-conformance.mjs | Closed | Hosted Play
EXP-SETUP-01 | Manage | Open local Explore host | Open http://127.0.0.1:8790/index.html | App loads; nav Decks/Library/Explore/Play | Loads; nav present | Pass |  | v3 screenshots Temp\cm-explore-uat |  |  | Closed | Explore
EXP-SETUP-99 | Manage | Console errors on Explore | Open Explore; check console | No errors | None | Pass |  | Explore |  |  | Closed | Explore
EXP-DES-01 | Design | Bare Explore three doors | Open bare #discover | Gap / Commander / Card doors | Present | Pass |  | Explore |  | crankmagic-discover.js | Closed | Explore
EXP-DES-02 | Design | Role chips + recents | Use chooser role chips; pick Sol Ring | Role chips; recents update | 7 role chips; Sol Ring in recents | Pass |  | Explore |  | crankmagic-discover.js | Closed | Explore
EXP-J1-02 | Manage | Bare #discover chooser not full graph | Open #discover with no scope | Chooser entry, not full graph | Chooser shown | Pass |  | Explore |  | crankmagic-discover.js | Closed | Explore
EXP-J1-02b | Manage | From a card door → Sol Ring | Door From a card → Sol Ring | #discover?card=Sol+Ring; graph centered; readable art | Pass | Pass |  | Explore |  | crankmagic-discover.js | Closed | Explore
EXP-J1-03 | Manage | Deep link scoped graph | Open scoped URL | Chooser skipped; Depth/Breadth/Loops | ~61 nodes; controls present | Pass |  | Explore |  | crankmagic-discover.js | Closed | Explore
EXP-J1-04 | Manage | Advanced Tools disclosure | Open Advanced Tools | Show Advanced Tools → Filters/Trace/Lens | Present and opens | Pass |  | Explore |  | crankmagic-discover.js | Closed | Explore
EXP-J1-05 | Manage | Canvas hover/click/inspect | Inspect Sol Ring on canvas | Inspect pane + Add/Buy; modes Navigate/Inspect/Select | Pass; readable card face | Pass |  | Explore |  | crankmagic-discover.js | Closed | Explore
EXP-J1-01 | Manage | Decks → deck → scoped Explore | Decks → open deck → Explore | Deck-scoped Discover | Fresh profile had no decks; fell through to bare chooser | Not run | S3 | Explore | Re-run with Load Live / seed deck in UAT profile | crankmagic-decks.js Trace; discover | Open | Explore
EXP-J2-01 | Manage | Sample facet/filter click | Click #cm-facet-bar facet | Facet applies while Advanced open | Facet in DOM; click hit non-visible control while Advanced collapsed; retry pending | Fail | S3 | Explore | Ensure facets usable when Advanced collapsed OR auto-expand Advanced when using facets; retry after toggle open | crankmagic-discover.js facet bar | Open | Explore
EXP-J2-02 | Manage | Role chip sample on chooser | Click role chips | Counts render | Pass | Pass |  | Explore |  |  | Closed | Explore
EXP-J3-01 | Build | Add from graph inspect | Inspect pane Add/Buy | add-card control present | Pass for Sol Ring | Pass |  | Explore |  | crankmagic-discover.js buyMenu | Closed | Explore
EXP-J3-02 | Build | Lens Swap on card-scoped graph | Look for lens-swap without deck scope | Swap if deck context; clear empty state otherwise | No lens-swap on non-deck graph — may be intentional | Partial | S3 | Explore | Document: Swap requires deck scope; when deck-scoped, expose Lens Swap / Swap into deck (ties to prior B-15) | crankmagic-discover.js | Open | Explore
EXP-J4-01 | Acquire | Wanted handoff from Explore | Inspect pane for Wanted CTA | Clear path to want-list / To buy entry from Explore | Live Explore agent: no standalone Wanted CTA on inspect. Box-mirror Add/Buy menu includes Main Deck / To Buy / Wants tribe (E-05 Pass) — handoff may exist inside Add/Buy rather than a Wanted label. | Partial | S3 | Explore | Verify Add/Buy → To Buy / Wants on Personal-HP inspect; if present, treat as Design C path and improve discoverability (not Gallery rename to Wanted). If missing on HP, add To buy handoff. | crankmagic-discover.js inspect/buyMenu | Open | Explore
E-01 | Explore entry | Explore entry vs Gallery Explore Entry design notes | Open http://127.0.0.1:8791/index.html#discover; compare three doors + OR READ BY ROLE pills to Gallery Explore Entry on :8792 | EXPLORE eyebrow; hero copy; three doors (FROM A DECK GAP / FROM A COMMANDER / FROM A CARD); role pills; optional recents when library seeded | Live entry matches Gallery structure (EXPLORE eyebrow, hero, three doors, OR READ BY ROLE pills with counts). Recents absent on empty box library. Deck-gap attempt toasts: You have no decks yet. | Pass |  | explore-entry.png; explore-gallery-entry.png; explore-discover-scoped.png | Optional Create-deck CTA on FROM A DECK GAP when decks=0 (toast already warns). | crankmagic-discover.js (explore entry / doors) | tested-box-mirror | Explore box-mirror
E-02 | Discover scope | Deck-scoped Discover when a deck exists; else global Explore | Attempt FROM A DECK GAP; when blocked, enter global Discover via Removal role pill | Deck-scoped graph when deck chosen; otherwise global Discover with lens context | No decks on box mirror → deck-scoped blocked. Global Discover via Removal: hash #discover?lens=Removal, h1=Discover, canvas graph, card inspector with Add/Buy. | Partial | S3 | explore-discover-scoped.png; explore-discover-removal.png; explore-card-or-chain.png | Re-run on Personal-HP with seeded decks for deck-scoped Discover + commander Trace. | crankmagic-discover.js (scope / Yours / lens) | tested-box-mirror | Explore box-mirror
E-03 | Filters / chains / cards | Random sample of filters, join terms, and card focus | Apply Removal lens; click flying join chip; inspect focused card; sample Trace tab | Filters narrow catalog; focused card updates; join chips filter; Trace/List available | Removal lens + flying mechanic chip applied; graph focused on Atraxa with labeled joins; Trace/Card Info tabs present. | Pass |  | explore-discover-removal.png; explore-filters-sampled.png; explore-card-or-chain.png; explore-filter-flying.png; explore-tab-trace.png |  | crankmagic-discover.js (facets / graph / terms) | tested-box-mirror | Explore box-mirror
E-04 | List ownership chips | List tab shows owned / in-deck chips | Open List tab in Discover pane; inspect legend and row chips | Owned/not-owned legend; in-deck chips when a deck is in Yours | Graph legend shows owned/not owned/loop-back. Inspector shows 0 owned · 0 reserved. List tab automation collided with Menu Publish your To Trade list. In-deck chips not exercised (no decks). | Partial | S3 | explore-filters-sampled.png; explore-list-ownership.png; explore-tab-list.png | Stable role=tab/data-testid on List; re-test with seeded deck. | crankmagic-discover.js (list pane) | tested-box-mirror | Explore box-mirror
E-05 | Add/Buy / Wanted | Attempt Add/Buy or Wanted from Discover card pane | Focus a card; open Add/Buy; observe Main Deck / To Buy / Wants items | Add/Buy menu offers deck add, buy-list, and/or wanted actions | Add/Buy present; menu items observed: Main Deck, To Buy, Wants tribe (product copy ≠ Gallery Wanted). | Pass |  | explore-add-buy-menu.png; explore-filters-sampled.png; explore-add-buy-wanted.png | Keep To Buy / Wants tribe vocabulary; do not force Gallery Wanted wording. | crankmagic-discover.js / change UI (Add/Buy menu) | tested-box-mirror | Explore box-mirror
E-06 | Focus retention | After Add/Buy attempt, remain in Discover | Open Add/Buy from Discover; check location.hash | Stay on #discover* after opening Add/Buy | Hash remained #discover?lens=Removal with Discover chrome retained while menu open. | Pass |  | explore-add-buy-menu.png; explore-discover-removal.png |  | crankmagic-discover.js | tested-box-mirror | Explore box-mirror

## Session notes
Amended with executor Decks/Library/Explore seed walk (Load Live) on box #311 + 37 PNGs in evidence/
Personal-HP write of evidence recommended; companion MD updated.
Explore deep Personal-HP walk still optional; E-01b already captured from seeded walk.

## Open remediations
Rank | Case | Severity | Defect | Recommended remediation | Code location | Source
1 | UAT-DELTA-03 | S1 | DELTA C–D table/Focus chrome — Not reached — Forge never launched | Unblock UAT-START-02 first | game/ui/review.* | Hosted Play
2 | UAT-GUEST-01 | S1 | Open human lobby for remote guests — 400 Remote guests unavailable — restart with Remote Guests enabled | Restart host via Desktop shortcut with -RemoteGuests; ensure cloudflared https | game/tools serve / launch ps1 | Hosted Play
3 | UAT-GUEST-02 | S1 | Fresh #table=&invite= guest link — Blocked by UAT-GUEST-01 | Unblock guestOrigin first |  | Hosted Play
4 | UAT-START-02 | S1 | Host+3AI Start→Forge — 400 spawnSync javac.exe ENOENT — C:\Users\robmi\CrankMagic\commander-runtime\jdk-17... missing; live idle | Restore commander-runtime JDK under CrankMagic (or retarget path to runtime\jdk-17.0.20.1+1 which exists under workbench/runtime); then re-Start | Forge spawn path config | Hosted Play
5 | CM-DS-001 | S2 | Shell rail structure — Structure OK; wordmark CrankOxanium vs Gallery Satoshi; dead .v-top/.v-layout{150px} CSS; subnav hover #fff | Remove dead Deep-Field/v-* CSS; align wordmark font to Gallery Satoshi; fix subnav hover | crankmagic-design.css; index.html shell | Workshop Design
6 | CM-DS-004 | S2 | No navy surfaces — Brass dominates live; design.css still ships navy v-cover gradients | Delete dead Deep-Field navy CSS so it cannot paint | crankmagic-design.css | Workshop Design
7 | CM-DS-005 | S2 | Focus ring aether — :focus-visible uses brass accent | Set focus-visible to --color-aether | crankmagic-design.css :focus-visible | Workshop Design
8 | CM-DS-009 | S2 | Library primary control height — Hierarchy OK but .compact 32px | Drop .compact on Library head; use 42px Gallery control height | crankmagic-collection.js / CSS .compact | Workshop Design
9 | CM-DS-010 | S2 | Decks grid 3-col — auto-fill minmax(260px,1fr) — density diverges | Lock grid-template-columns: repeat(3, minmax(0,1fr)) at desktop | crankmagic.css deck tiles grid | Workshop Design
10 | CM-DS-011 | S2 | Deck page h1 / bento — Largely matches; global h1 36/700 still in design.css (override race) | Remove dead global h1 36/700 rule | crankmagic-design.css h1 | Workshop Design
11 | CM-DS-012 | S2 | Library type/spacing scale — head+row .compact 32px undershoot | Restore 42px control scale on Library chrome | crankmagic.css .compact | Workshop Design
12 | DR-P05 | S2 | Center table tools: End table / force-advance — Still has Start/Stop; missing End table/force-advance | Align Host tools to DELTA: End table + force-advance; clarify Start/Stop vs auto-launch | crankmagic-game.js host tools | Play Design
13 | DR-P09 | S2 | Dual path Desktop shortcut vs CrankMagic\repo — Desktop vs repo dual path risk | Unify: shortcut WorkingDirectory → C:\Users\robmi\CrankMagic\repo (or document single path); retire commander-phase-c if obsolete | Start Game.lnk; launch ps1 | Play Design
14 | E-01b | S2 | Explore route naming / cold load — None | Keep Explore entry as default when no focus; rename Discover→Explore in pageHead/HELP; show entry while graph warms or progress on entry chrome | crankmagic-discover.js views.discover pageHead("Discover") | Executor Decks/Library
15 | EXP-J4-01 | S2 | Wanted handoff from Explore — No Wanted CTA; Add/Buy only; body has no Wanted | Add To buy / want-list handoff from inspect (Design C) without Gallery renaming to Wanted; or confirm intentional Add/Buy-only | crankmagic-discover.js inspect/buyMenu | Explore
16 | L-02 | S2 | Sheet view editable numeric cells — None | Implement in-place numeric editors per Gallery Sheet behaviour (inputmode=numeric, commit on Enter/Tab) | crankmagic-collection.js sheet view; crankmagic.css sheet cells | Executor Decks/Library
17 | LIB-06 | S2 | Wanted on To buy tab (Design C) — Shop filter excludes kind=entry; buy count = need only; entry counted as Watched | Design C: include want-list (group:to-buy entry) lots in To buy shop filter + buy tab/KPI counts; do NOT rename UI to Wanted for Gallery — Gallery/wireframes use To buy / Buy list only (0 hits for Wanted). | crankmagic-collection.js rows/tabCounts/statsHTML | Collection truth
18 | LIB-11 | S2 | Gallery chrome pixels — Gallery HTML did not paint in box Chrome (support.js React unpkg ERR_TUNNEL). Expectations from source only. Live pager Prev/Next; prefs have 60/120/All. Not a product visual contradict. | Optional: expose 60/120/All page-size segment like Gallery footer; keep LIB-11 Open as incomplete visual compare (infra), not defect | crankmagic-design.css / cardsHead | Collection truth
19 | UAT-ENV-02 | S2 | guestOrigin https for remote guests — guestOrigin=http://127.0.0.1:8769; cloudflared not running; remoteGuestsAvailable=false | Relaunch Desktop Start Game with Remote Guests so cloudflared publishes https guestOrigin | launch-crankmagic-online.ps1 -RemoteGuests | Hosted Play
20 | CM-DS-002 | S3 | Shell <760 phone — Horizontal sticky sidebar; current ≠ raised pill; 46px trio not verified | Match Gallery phone current=raised; verify sticky trio | crankmagic.css shell media | Workshop Design
21 | D-01b | S3 | Deck tiles + New deck primary + Compare — None | Pin Decks grid to repeat(3, minmax(0,1fr)) at desktop; rename Compare to match Gallery or keep selected-count pattern but show enabled secondary when ≥2 picks; radius 22px | crankmagic.css .cm-deck-grid {repeat(auto-fill,minmax(260px,1fr))} | Executor Decks/Library
22 | D-03b | S3 | Rail sub-pages Ready to add / Make the change under open deck — None | Render C.SUBNAV.decks Ready to add / Make the change indented under current deck in rail on all deck tabs | crankmagic-decks.js C.SUBNAV.decks; index.html rail render | Executor Decks/Library
23 | DR-P02 | S3 | Lobby geometry 2×2 vs legacy card-row PNGs — Repo has 2b slice; older PNGs still card-row — dual visual truth | Retire/archive card-row UAT shots; single geometry source of truth | crankmagic-game.js lobby layout | Play Design
24 | DR-P03 | S3 | Seat chrome commander-forward vs under-bars hero — Under-bars hero path still present in older artifacts | Confirm with Trey whether under-bars/Deck Summary still locked; else treat as legacy | crankmagic-game.js seat render | Play Design
25 | DR-P06 | S3 | Change deck 2d tabs Saved/Lab/Bring + Use-at-Seat — Not matching 2d | Implement Change deck 2d structure (Claude Play lane) | crankmagic-game.js change deck | Play Design
26 | E-BLOCK-01 | S3 | Explore live Personal-HP walk (agent) — Explore agent blocked; box executor covered E-01b on seeded Load Live instead | Optional follow-up Explore deep sample on HP | crankmagic-discover.js | Explore
27 | EXP-J1-01 | S3 | Decks → deck → scoped Explore — Fresh profile had no decks; fell through to bare chooser | Re-run with Load Live / seed deck in UAT profile | crankmagic-decks.js Trace; discover | Explore
28 | EXP-J2-01 | S3 | Sample facet/filter click — Facet in DOM; click hit non-visible control while Advanced collapsed; retry pending | Ensure facets usable when Advanced collapsed OR auto-expand Advanced when using facets; retry after toggle open | crankmagic-discover.js facet bar | Explore
29 | EXP-J3-02 | S3 | Lens Swap on card-scoped graph — No lens-swap on non-deck graph — may be intentional | Document: Swap requires deck scope; when deck-scoped, expose Lens Swap / Swap into deck (ties to prior B-15) | crankmagic-discover.js | Explore
30 | L-06 | S3 | Cross-surface count vocabulary — None | Align head sentence with KPI definitions (or footnote what "copies you own" includes) | crankmagic-collection.js pageHead / counters | Executor Decks/Library
31 | LIB-01 | S3 | Library head actions — pageHead order is Add cards (primary) · Import list · More | Reorder head buttons to match Gallery Library | crankmagic-collection.js cardsHead | Collection truth
32 | LIB-04 | S3 | Card cell mana marks — rowMark uses mana COST not identity; land L OK | Render identity pips per gallery; keep land mark | crankmagic-collection.js rowMark | Collection truth
33 | M-LIVE-1 | S3 | Live browser Measure walk — :8768/:8769 200; Playwright walk not run (node not on Shell PATH) | Optional live click walk when Playwright available |  | Measure
34 | UAT-DELTA-01 | S3 | DELTA B.5 No Launch vs live Start+countdown — Live has Start + countdown (Rob request per Claude) — intentional product delta vs wireframe | Update DELTA/wireframe to match locked Start+countdown OR revert UI to auto-launch — Trey decide | docs/design DELTA §B.5 | Hosted Play
35 | UAT-DELTA-02 | S3 | DELTA B.4 Choose mat / fan / quadrant sea — Claude claims done; Hosted Play no CDP re-verify | Visual re-verify with CDP | crankmagic-game.js | Hosted Play
36 | UAT-ENV-04 | S3 | CDP :9222 browser drive — timeout — no CDP browser | Attach Chrome with --remote-debugging-port=9222 or install Playwright for Cursor helper |  | Hosted Play
37 | UAT-WF-02 | S3 | lobby-permutations Playwright — Playwright not installed in Cursor node helper | Install Playwright in UAT helper or use Claude prior green log as provisional |  | Hosted Play
38 | W-DECKS-02 | S3 | Compare two decks — Gallery Decks head shows Compare (secondary) + New deck (primary) over 3-col poster grid (gallery-decks.png). Live empty Decks has New deck + Import a backup only (no Compare). Live with decks uses Compare selected (checkbox-gated). | Align Decks head actions to Gallery Compare + New deck hierarchy; keep multi-select if needed | crankmagic-decks.js pageHead | Workshop IA
39 | W-DECKS-03 | S3 | Scan deck library tiles — Gallery Decks = 3-col posters + Compare + New deck + summary line (gallery-decks.png). Live empty = hero “Build it. Make it yours.” + New deck / Import a backup + card fan (live-decks.png). No live populated Decks grid shot yet. | Screenshot side-by-side with Gallery Decks.dc.html at 1280px; close spacing/radius gaps | crankmagic-decks.js views.decks + CSS tiles | Workshop IA
40 | W-DECKS-04 | S3 | Read Decks rail subnav — Rail sub-link truncates to “How a deck comes to…” | Widen rail / wrap / shorten label; verify at 216px | index.html + CSS rail | Workshop IA
41 | W-DECKS-05 | S3 | Empty Decks first-run — Gallery Decks = 3-col posters + Compare + New deck + summary line (gallery-decks.png). Live empty = hero “Build it. Make it yours.” + New deck / Import a backup + card fan (live-decks.png). No live populated Decks grid shot yet. | Reconcile empty state with Gallery empty/populated patterns | crankmagic-decks.js empty showcase | Workshop IA
42 | W-DS-01 | S3 | Design-system palette — Live deck page + Decks empty use warm brass primary (#d9a441-class) on near-black brown; Gallery matches. CSS still has leftover hex sweep work; no navy primary chrome in these shots (logo wand blue only). | Finish literal→token sweep; accept DoD screenshots vs Gallery | crankmagic.css / crankmagic-design.css | Workshop IA
43 | W-DS-02 | S3 | Shell structure — Live still uses cm-layout 216px rail — full Gallery shell (Menu foot / header removal) Not run pending screenshot | Screenshot shell vs Gallery; implement remaining shell steps from IMPLEMENTATION-GUIDE §2 | index.html + crankmagic.css shell | Workshop IA
44 | W-PAGE-02 | S3 | Overview bento next-step — Live Krenko draft Overview shows NEXT / PROGRESS / COST bento; commander art missing (broken image) on brand-new draft; Gallery shows full art + richer NEXT copy for populated deck | Ensure commander art resolves on Create draft; keep bento structure; polish NEXT copy for Defining vs Playable states | crankmagic-decks.js overview + card image resolve | Workshop IA
45 | A-00 | S4 | Empty Decks landing before Load Live — None | Optional empty-state notes in handoff; ensure Load Live discoverable (Menu path works) | crankmagic-decks.js empty branch | Executor Decks/Library
46 | D-08 | S4 | Compare decks affordance — None | Match Gallery label "Compare"; allow entry to compare flow or explain disabled state in UI | crankmagic-decks.js compare control | Executor Decks/Library
47 | DR-P07 | S4 | Choose mat depth — Partial depth | Deepen Choose mat to wireframe options | crankmagic-game.js mat | Play Design
48 | DR-P08 | S4 | Shell Brass/Slate vs residual navy — Residual navy on older shots; live may be partial | Sweep Play chrome for leftover navy; apply design-system tokens | crankmagic.css / crankmagic-design.css | Play Design
49 | W-PLAY-01 | S4 | Play entry from Decks domain — Out of Workshop deep UAT this pass (Play>Lobby>Game owned elsewhere); nav label Play present | Defer to Play/Hosted Play UAT lanes | Play routes | Workshop IA
50 | DR-P10 |  | Table 2e/2f live canvas — Not run (IN FLUX / Forge session) | Re-run after Claude Play merge + Forge available | game/ui/review.* | Play Design
51 | UAT-SEAT-01 |  | Human/AI/Unused seat UI — NOT DRIVEN (no CDP); Claude log claimed prior green | Re-drive when CDP available | crankmagic-game.js | Hosted Play